## Task
AI BASED VIDEO EMAIL MARKETING TOOL
Milestone 1 – Video Editing Service Start from 20-12-2022 to 10-01-2023
Backend Task | FrontendTask
Create Database | Create Register & Login Desing For Admin
Create AdminRegisterAPI, UserRegister | Choose button for upload category & video templates
Create AdminLoginAPI,UserLogin | Create user Register and login page
Create Category and Sub CategoryStore API | dashboard and show the videos in frontend
Create Video Store API | download the vdo if user choose with category
create payment method | ?
Milestone 2 – Video Editing Service Start from 11-01-2023 to 20-02-2023
Backend Task | FrontendTask
Create Marketing service for users API | NA
Create upload csv file with details of customers. API | Create design for Upload CSV file
Download CSV template API | create design for download empty template of csv file
Make a mail for customers API | NA
Rendering service with notifications API | Create design for notification
Milestone 3 – Video Editing Service Start from 21-01-2023 to 31-03-2023
Backend Task | FrontendTask
create API for vdo appended | NA
create API for Get image and details in Linkedin | NA
create API for develop message and send it to customers mail | NA
create API for developing tracking process. | Create design for tracking process for admin and user

## DB Structure
TableNames | Columns1 | Columns2 | Columns3 | Columns4 | Columns5 | Columns6 | Columns7 | Columns8 | Columns9 | Columns10
AdminPanelLogin | Columns1: AdminUserName; Columns2: AdminPassword; Columns3: AdminMail; Columns4: MobileNumber; Columns5: Date
AdminCategory | Columns1: CatName; Columns2: CatId; Columns3: CreatedDate; Columns4: InfoOfCategory; Columns5: AdminID(FK)
AdminUploadVideos | VideoTemplate | CatId (FK) | UploadedDate | AdminId(FK) | subCatID(FK) | VideoDetails | VideoPrice | Offer | Discount | Activity status
AdminSubCategory | Columns1: CatId(FK); Columns2: SubCategory_name; Columns3: subCatId
UserRegister | Username | WorkMail | Password | ConfirmPassword | Authentication | ID(PK)
UserLogin | Columns1: Username; Columns2: Password; Columns3: Date; Columns4: RegisterId(FK)
UserCategoryHistory | Columns1: UserID(FK); Columns2: Video; Columns3: Category; Columns4: ChooseDate; Columns5: VideoTitle
UserSelectedCategory | Columns1: UserId(FK); Columns2: CategoryID(FK)
UserGetCSVTemplate | Columns1: UserId(FK); Columns2: CSVFile
PaymentTable | Columns1: UserID(FK); Columns2: PaymentMethod; Columns3: PaymentUser